## Tracker
Feature ID | Feature Name | Area / Module | Source File(s) | Route / Screen / Command / Entry Point | User Type | User Story | Expected Behaviour | Actual Behaviour | Status | Test Type | Test Steps | Test Result | Error / Bug Found | Severity | Fix Required | Fix Implemented | Files Changed | Commit Hash | Retest Steps | Retest Result | Final Status | Product Decision Needed | Notes | Original Prompt
WEB-001 | Desktop primary navigation | Landing / Navigation | index.html; tests/landing-page.mjs | / | First-time visitor | As a first-time visitor, I want a concise navigation bar so that I can reach the product, Apple proof, trust information, MCP documentation, and research quickly. | Five destinations plus one Run Apple action are visible, correctly labeled, keyboard reachable, and link to valid targets. | Observed behavior matched the tracker-backed expectation in the discovery test pass. | Verified | Automated UI | Open / at 1440x1000; count navigation actions; tab through links; verify href targets and focus visibility. | PASS — qa_evidence/logs/feature_ui_audit.json; qa_evidence/lighthouse/landing-desktop/report.json |  |  | No |  |  |  |  | Not required in discovery pass. | Verified | No | Discovery evidence: qa_evidence/logs/feature_ui_audit.json; qa_evidence/lighthouse/landing-desktop/report.json | /goal implement the cutting edge UI rich with graphics and easy to understand
WEB-002 | Mobile navigation menu | Landing / Navigation | index.html; tests/landing-page.mjs | / at 390x844 | Mobile visitor | As a mobile visitor, I want a compact menu so that I can reach every primary destination without horizontal overflow. | Menu opens and closes, exposes all primary links, updates aria-expanded, and causes no horizontal overflow. | Accessible name now includes the visible “Menu” label. | Fixed | Automated UI | Open / at 390x844; activate Menu; inspect class and aria-expanded; verify links; measure document overflow. | FAIL — qa_evidence/lighthouse/landing-mobile/report.json ¦ FIX VERIFIED | Mobile menu displays “Menu” but its aria-label is “Toggle navigation”; Lighthouse flags label-content-name-mismatch. | Medium | Yes | Accessible name now includes the visible “Menu” label. | index.html | 4883949 | Open / at 390x844; activate Menu; inspect class and aria-expanded; verify links; measure document overflow. | PASS — Lighthouse mobile: accessibility 100, 55 passed, 0 failed. | Verified | No | Pre-fix discovery evidence: qa_evidence/lighthouse/landing-mobile/report.json ¦ Retest evidence: qa_evidence/lighthouse/retest-landing-mobile/report.json ¦ Stable pre-fix finding: qa_evidence/logs/discovery_findings.json | /goal implement the cutting edge UI rich with graphics and easy to understand
WEB-003 | Apple-first hero comprehension | Landing / Hero | index.html; tests/landing-page.mjs | /#top | Research prospect | As a research prospect, I want to understand DeltaSignal within ten seconds so that I know what it does and why Apple is shown. | Hero identifies DeltaSignal as evidence infrastructure, Apple as a public reference case, controlled read-only evidence flow, concrete output, and non-advice boundary. | Observed behavior matched the tracker-backed expectation in the discovery test pass. | Verified | Automated UI | Inspect first viewport at 1440x1000; assert required comprehension phrases; capture screenshot; run accessibility audit. | PASS — qa_evidence/logs/feature_ui_audit.json; qa_evidence/lighthouse/landing-desktop/report.json |  |  | No |  |  |  |  | Not required in discovery pass. | Verified | No | Discovery evidence: qa_evidence/logs/feature_ui_audit.json; qa_evidence/lighthouse/landing-desktop/report.json | /goal implement the cutting edge UI rich with graphics and easy to understand
WEB-004 | Hero primary actions | Landing / Hero | index.html; tests/landing-page.mjs | /#top | Research prospect | As a prospect, I want two clear next steps so that I can run a sample AAPL report or understand how evidence reaches agents. | Exactly two hero actions are present, visually prominent, descriptive, and point to the AAPL demo and MCP surface. | Observed behavior matched the tracker-backed expectation in the discovery test pass. | Verified | Automated UI | Count hero links; inspect accessible names and hrefs; activate local AAPL link and confirm destination loads. | PASS — qa_evidence/logs/feature_ui_audit.json; qa_evidence/lighthouse/landing-desktop/report.json |  |  | No |  |  |  |  | Not required in discovery pass. | Verified | No | Discovery evidence: qa_evidence/logs/feature_ui_audit.json; qa_evidence/lighthouse/landing-desktop/report.json | /goal implement the cutting edge UI rich with graphics and easy to understand
WEB-005 | Evidence run preview card | Landing / Hero | index.html; tests/landing-page.mjs | /#top | Financial analyst | As an analyst, I want a compact preview of the evidence run so that I understand the source-to-packet path before clicking. | Card shows source, governance, controlled gateway, agents, inspectable packet, status, provenance, missingness, and non-advice language with legible text. | Observed behavior matched the tracker-backed expectation in the discovery test pass. | Verified | Manual UI | Inspect hero card at desktop and mobile; verify all stages and semantic colors; check text contrast and clipping. | PASS — qa_evidence/logs/feature_ui_audit.json; qa_evidence/lighthouse/landing-desktop/report.json |  |  | No |  |  |  |  | Not required in discovery pass. | Verified | No | Discovery evidence: qa_evidence/logs/feature_ui_audit.json; qa_evidence/lighthouse/landing-desktop/report.json | /goal implement the cutting edge UI rich with graphics and easy to understand
WEB-006 | Operational proof strip | Landing / Trust strip | index.html; tests/landing-page.mjs | / below hero | Compliance buyer | As a compliance buyer, I want immediate operating boundaries so that I can distinguish reference evidence, access mode, and non-advice status. | Reference case date, filing-backed state, read-only MCP mode, and non-advice boundary are visible with distinct semantic rails. | Observed behavior matched the tracker-backed expectation in the discovery test pass. | Verified | Automated UI | Assert four proof-strip cells and required labels; verify semantic state attributes and mobile stacking. | PASS — qa_evidence/logs/feature_ui_audit.json; qa_evidence/lighthouse/landing-desktop/report.json |  |  | No |  |  |  |  | Not required in discovery pass. | Verified | No | Discovery evidence: qa_evidence/logs/feature_ui_audit.json; qa_evidence/lighthouse/landing-desktop/report.json | /goal implement the cutting edge UI rich with graphics and easy to understand
WEB-007 | Simplified architecture overview | Landing / Architecture | index.html; tests/landing-page.mjs | /#agent-architecture | Nontechnical buyer | As a nontechnical buyer, I want a simple architecture overview so that I can understand input, governance, controlled delivery, review, and output. | Five large, legible modules use explicit INPUT → GOVERN → CONTROLLED DELIVERY → REVIEW → OUTPUT labels, arrows, graphics, and plain language. | Observed behavior matched the tracker-backed expectation in the discovery test pass. | Verified | Automated UI | Scroll to architecture; count five modules; assert labels and explanations; measure typography; capture desktop/mobile screenshots. | PASS — qa_evidence/logs/feature_ui_audit.json; qa_evidence/lighthouse/landing-desktop/report.json |  |  | No |  |  |  |  | Not required in discovery pass. | Verified | No | Discovery evidence: qa_evidence/logs/feature_ui_audit.json; qa_evidence/lighthouse/landing-desktop/report.json | /goal implement the cutting edge UI rich with graphics and easy to understand
WEB-008 | Full architecture disclosure | Landing / Architecture | index.html; tests/landing-page.mjs | /#agent-architecture | Technical evaluator | As a technical evaluator, I want to expand the specialist architecture so that I can inspect coordinator, agents, review, Gemini synthesis, and output roles. | Detail is collapsed by default, opens from an accessible control, contains four explicitly labeled AI specialists, differentiates runtime/model/agents, and can close again. | Observed behavior matched the tracker-backed expectation in the discovery test pass. | Verified | Automated UI | Verify initial collapsed state; activate toggle twice; inspect aria-expanded, specialist count, role labels, glyphs, and full-graph visibility. | PASS — qa_evidence/logs/feature_ui_audit.json; qa_evidence/lighthouse/landing-desktop/report.json |  |  | No |  |  |  |  | Not required in discovery pass. | Verified | No | Discovery evidence: qa_evidence/logs/feature_ui_audit.json; qa_evidence/lighthouse/landing-desktop/report.json | /goal implement the cutting edge UI rich with graphics and easy to understand
WEB-009 | Platform capability tabs | Landing / Product | index.html; tests/landing-page.mjs | /#platform | Agent builder | As an agent builder, I want to compare evidence, ATLAS-7, MCP, and Google-agent capabilities so that I can understand the modular product. | Four keyboard-operable tabs switch one clear capability panel and retain understandable bullets and semantic colors. | Observed behavior matched the tracker-backed expectation in the discovery test pass. | Verified | Automated UI | Count tabs; click each; assert title/body changes and aria-selected; test keyboard focus; inspect mobile layout. | PASS — qa_evidence/logs/feature_ui_audit.json; qa_evidence/lighthouse/landing-desktop/report.json |  |  | No |  |  |  |  | Not required in discovery pass. | Verified | No | Discovery evidence: qa_evidence/logs/feature_ui_audit.json; qa_evidence/lighthouse/landing-desktop/report.json | /goal implement the cutting edge UI rich with graphics and easy to understand
WEB-010 | Apple interactive-demo promotion | Landing / Apple proof | index.html; tests/landing-page.mjs | /#demo | Prospective client | As a prospective client, I want a visual Apple demo preview so that I can choose interactive, presentation, or recording-plan modes. | Preview graphic is not cropped, explanatory copy is clear, and all three actions link to valid assets. | Observed behavior matched the tracker-backed expectation in the discovery test pass. | Verified | Automated UI | Inspect demo image dimensions and overflow; verify three actions and targets; load interactive and presentation destinations. | PASS — qa_evidence/logs/feature_ui_audit.json; qa_evidence/lighthouse/landing-desktop/report.json |  |  | No |  |  |  |  | Not required in discovery pass. | Verified | No | Discovery evidence: qa_evidence/logs/feature_ui_audit.json; qa_evidence/lighthouse/landing-desktop/report.json | /goal implement the cutting edge UI rich with graphics and easy to understand
WEB-011 | Governed workflow sequence | Landing / Workflow | index.html; tests/landing-page.mjs | /#workflow | Financial researcher | As a financial researcher, I want to see the governed sequence so that I understand how source data becomes a reviewed packet. | Six sequential cards show Source, Govern, Route, Delegate, Review, Deliver with plain-language notes and readable responsive layout. | Observed behavior matched the tracker-backed expectation in the discovery test pass. | Verified | Automated UI | Count six steps; verify order and explanations; inspect desktop and mobile layout for clipping and sequence clarity. | PASS — qa_evidence/logs/feature_ui_audit.json; qa_evidence/lighthouse/landing-desktop/report.json |  |  | No |  |  |  |  | Not required in discovery pass. | Verified | No | Discovery evidence: qa_evidence/logs/feature_ui_audit.json; qa_evidence/lighthouse/landing-desktop/report.json | /goal implement the cutting edge UI rich with graphics and easy to understand
WEB-012 | Audience path cards | Landing / Conversion | index.html; tests/landing-page.mjs | /#competition-proof | Visitor with distinct intent | As a visitor, I want a path matching my intent so that I can use, build, read, or partner without searching. | Four path cards clearly separate use, build, read, and partner actions with valid destinations and consistent visual hierarchy. | Observed behavior matched the tracker-backed expectation in the discovery test pass. | Verified | Automated UI | Count four cards; assert labels/actions/hrefs; inspect hover/focus; verify mobile stacking. | PASS — qa_evidence/logs/feature_ui_audit.json; qa_evidence/lighthouse/landing-desktop/report.json |  |  | No |  |  |  |  | Not required in discovery pass. | Verified | No | Discovery evidence: qa_evidence/logs/feature_ui_audit.json; qa_evidence/lighthouse/landing-desktop/report.json | /goal implement the cutting edge UI rich with graphics and easy to understand
WEB-013 | Trust methodology cards | Landing / Trust | index.html; tests/landing-page.mjs | /#trust | Compliance buyer | As a compliance buyer, I want methodology boundaries so that I can judge filing provenance, point-in-time safety, missingness, and agent readiness. | Four trust cards explain boundaries and link to architecture, MCP surface, and agent contract. | Observed behavior matched the tracker-backed expectation in the discovery test pass. | Verified | Automated UI | Count cards; assert required concepts and three resource links; validate link responses where network permits. | PASS — qa_evidence/logs/feature_ui_audit.json; qa_evidence/lighthouse/landing-desktop/report.json |  |  | No |  |  |  |  | Not required in discovery pass. | Verified | No | Discovery evidence: qa_evidence/logs/feature_ui_audit.json; qa_evidence/lighthouse/landing-desktop/report.json | /goal implement the cutting edge UI rich with graphics and easy to understand
WEB-014 | Final conversion actions | Landing / CTA | index.html; tests/landing-page.mjs | / final CTA | Prospective client | As a prospective client, I want clear final actions so that I can run the reference, tour the product, discuss a project, inspect Cloud Run, or inspect source. | Actions are distinguishable, keyboard accessible, and point to correct destinations without misleading execution claims. | Cloud Run now continues the Apple-first Evidence OS narrative and labels HUT as a second research-memory proof. | Fixed | Automated UI | Enumerate CTA links and accessible names; validate local links; inspect visual priority and mobile wrapping. | FAIL — qa_evidence/screenshots/cloud-root-1440x1000.png ¦ FIX VERIFIED | The final Cloud Run action opens a stale competition-branded, HUT-first surface instead of continuing the Apple-first Evidence OS narrative. | High | Yes | Cloud Run now continues the Apple-first Evidence OS narrative and labels HUT as a second research-memory proof. | cmd/server/demo_ui.go; cmd/server/demo_ui_test.go | 4883949 | Enumerate CTA links and accessible names; validate local links; inspect visual priority and mobile wrapping. | PASS — all final actions resolve into coherent, explicitly prioritized product surfaces. | Verified | No | Pre-fix discovery evidence: qa_evidence/screenshots/cloud-root-1440x1000.png ¦ Retest evidence: qa_evidence/screenshots/cloud-root-1440x1000.png; qa_evidence/logs/retest-go-test-all.log ¦ Stable pre-fix finding: qa_evidence/logs/discovery_findings.json | /goal implement the cutting edge UI rich with graphics and easy to understand
WEB-015 | Footer provenance and resources | Landing / Footer | index.html; tests/landing-page.mjs | / footer | Technical evaluator | As a technical evaluator, I want durable resource links and the non-advice boundary so that I can inspect evidence and implementation details. | Footer contains non-advice text plus comprehension audit, A2A spec, architecture, and GitHub links. | Observed behavior matched the tracker-backed expectation in the discovery test pass. | Verified | Automated UI | Inspect footer text and hrefs; load local resources; verify contrast and mobile wrapping. | PASS — qa_evidence/logs/feature_ui_audit.json; qa_evidence/lighthouse/landing-desktop/report.json |  |  | No |  |  |  |  | Not required in discovery pass. | Verified | No | Discovery evidence: qa_evidence/logs/feature_ui_audit.json; qa_evidence/lighthouse/landing-desktop/report.json | /goal implement the cutting edge UI rich with graphics and easy to understand
WEB-016 | Responsive and accessible landing | Landing / Cross-cutting | index.html; tests/landing-page.mjs | / responsive states | All visitors | As a visitor using different devices or assistive settings, I want a readable and motion-safe interface so that I can use every feature. | No horizontal overflow at 390px or 1440px, semantic landmarks and accessible names exist, contrast passes, and reduced motion disables nonessential animations. | Observed behavior matched the tracker-backed expectation in the discovery test pass. | Verified | Automated UI | Run Playwright desktop/mobile/reduced-motion checks and Lighthouse accessibility/best-practices audits; record scores and failures. | PASS — qa_evidence/logs/feature_ui_audit.json; qa_evidence/lighthouse/landing-desktop/report.json |  |  | No |  |  |  |  | Not required in discovery pass. | Verified | No | Discovery evidence: qa_evidence/logs/feature_ui_audit.json; qa_evidence/lighthouse/landing-desktop/report.json | /goal implement the cutting edge UI rich with graphics and easy to understand
WEB-017 | Functional module color differentiation | Landing / Visual system | index.html; tests/landing-page.mjs | / content modules | Visual learner | As a visual learner, I want functional modules to have distinct backgrounds so that I can scan the system quickly. | Architecture, platform, demo, workflow, audience, and trust areas have distinct restrained dark color fields while maintaining consistent semantic color and contrast. | Observed behavior matched the tracker-backed expectation in the discovery test pass. | Verified | Manual UI | Capture full-page desktop screenshot; compare section backgrounds and labels; run contrast audit; verify no visual ambiguity or excessive decoration. | PASS — qa_evidence/logs/feature_ui_audit.json; qa_evidence/lighthouse/landing-desktop/report.json |  |  | No |  |  |  |  | Not required in discovery pass. | Verified | No | Discovery evidence: qa_evidence/logs/feature_ui_audit.json; qa_evidence/lighthouse/landing-desktop/report.json | /goal implement the cutting edge UI rich with graphics and easy to understand
TOUR-001 | Product tour activation | Product tour | index.html; tests/landing-page.mjs | /?tour=1 | Prospective client | As a prospective client, I want a focused product tour so that I can understand the product without scrolling the full site. | Query activation opens a full-viewport presentation led by the Apple reference with no page overflow. | Tour slide 4 now explicitly labels HUT as the second proof beyond the flagship Apple workflow. | Fixed | Automated UI | Open /?tour=1 at 1920x1080; assert theater visible, Apple opening, one stage, no overflow. | FAIL — qa_evidence/logs/feature_ui_audit.json ¦ FIX VERIFIED | Slide 4 switches from the Apple reference to HUT without an explicit ‘second proof’ transition, weakening the Apple-first story. | Medium | Yes | Tour slide 4 now explicitly labels HUT as the second proof beyond the flagship Apple workflow. | index.html | 4883949 | Open /?tour=1 at 1920x1080; assert theater visible, Apple opening, one stage, no overflow. | PASS — six-slide navigation preserves the Apple-first story and explains the issuer transition. | Verified | No | Pre-fix discovery evidence: qa_evidence/logs/feature_ui_audit.json ¦ Retest evidence: qa_evidence/logs/retest-feature_ui_audit.json ¦ Stable pre-fix finding: qa_evidence/logs/discovery_findings.json | /goal implement the cutting edge UI rich with graphics and easy to understand
TOUR-002 | Tour previous and next navigation | Product tour | index.html; tests/landing-page.mjs | /?tour=1 | Presentation viewer | As a presentation viewer, I want previous and next controls and arrow-key support so that I can move through the story predictably. | Controls and arrow keys move exactly one slide, disable at boundaries, and update title/index/progress. | Observed behavior matched the tracker-backed expectation in the discovery test pass. | Verified | Automated UI | Activate next/previous buttons and ArrowRight/ArrowLeft; verify slide text, disabled states, and progress. | PASS — qa_evidence/logs/feature_ui_audit.json; qa_evidence/screenshots/tour-final-1920x1080.png |  |  | No |  |  |  |  | Not required in discovery pass. | Verified | No | Discovery evidence: qa_evidence/logs/feature_ui_audit.json; qa_evidence/screenshots/tour-final-1920x1080.png | /goal implement the cutting edge UI rich with graphics and easy to understand
TOUR-003 | Tour autoplay | Product tour | index.html | /?tour=1 | Presenter | As a presenter, I want autoplay so that I can record or demonstrate a paced narrative hands-free. | Autoplay advances at a stable interval, toggles to pause, resets from final slide, and stops at the end. | Observed behavior matched the tracker-backed expectation in the discovery test pass. | Verified | Automated UI | Start autoplay; wait for slide advance; pause; restart at final slide; verify labels and timer stop. | PASS — qa_evidence/logs/feature_ui_audit.json; qa_evidence/screenshots/tour-final-1920x1080.png |  |  | No |  |  |  |  | Not required in discovery pass. | Verified | No | Discovery evidence: qa_evidence/logs/feature_ui_audit.json; qa_evidence/screenshots/tour-final-1920x1080.png | /goal implement the cutting edge UI rich with graphics and easy to understand
TOUR-004 | Tour exit behavior | Product tour | index.html; tests/landing-page.mjs | /?tour=1 | Presentation viewer | As a viewer, I want to exit the tour by button or Escape so that I can return to the landing page immediately. | Exit button and Escape leave presentation mode, restore clean URL state, and return to top. | Observed behavior matched the tracker-backed expectation in the discovery test pass. | Verified | Automated UI | Exit by button and by Escape in separate runs; verify theater removed, URL query cleared, scroll position reset. | PASS — qa_evidence/logs/feature_ui_audit.json; qa_evidence/screenshots/tour-final-1920x1080.png |  |  | No |  |  |  |  | Not required in discovery pass. | Verified | No | Discovery evidence: qa_evidence/logs/feature_ui_audit.json; qa_evidence/screenshots/tour-final-1920x1080.png | /goal implement the cutting edge UI rich with graphics and easy to understand
TOUR-005 | Tour recording layout | Product tour | index.html; scripts/record-product-tour.mjs | /?tour=1 at 1920x1080 | Content producer | As a content producer, I want a recording-safe layout so that slides remain readable in a 16:9 video. | All slides fit 1920x1080 without overflow, controls remain visible, and essential text is legible. | Observed behavior matched the tracker-backed expectation in the discovery test pass. | Verified | Automated UI | Visit every slide at 1920x1080; measure overflow and bounding boxes; capture screenshots. | PASS — qa_evidence/logs/feature_ui_audit.json; qa_evidence/screenshots/tour-final-1920x1080.png |  |  | No |  |  |  |  | Not required in discovery pass. | Verified | No | Discovery evidence: qa_evidence/logs/feature_ui_audit.json; qa_evidence/screenshots/tour-final-1920x1080.png | /goal implement the cutting edge UI rich with graphics and easy to understand
AAPL-001 | AAPL demo navigation | AAPL Client Demo / Navigation | client-demo/google-cloud-aapl/Google_Cloud_AAPL_DeltaSignal_MCP_Client_Demo_2026_08_06.html; client-demo/google-cloud-aapl/test-interactive-walkthrough.mjs | /client-demo/google-cloud-aapl/ | Client evaluator | As a client evaluator, I want links to the main site, MCP surface, and source so that I can inspect the demo context. | Navigation is visible, legible, and links to correct public destinations. | Observed behavior matched the tracker-backed expectation in the discovery test pass. | Verified | Automated UI | Load demo; inspect top navigation labels/hrefs; validate local main-site return and external URLs. | PASS — qa_evidence/logs/aapl-walkthrough-test.log; qa_evidence/logs/feature_ui_audit.json |  |  | No |  |  |  |  | Not required in discovery pass. | Verified | No | Discovery evidence: qa_evidence/logs/aapl-walkthrough-test.log; qa_evidence/logs/feature_ui_audit.json | /goal implement the cutting edge UI rich with graphics and easy to understand
AAPL-002 | Six-stage architecture tabs | AAPL Client Demo / Walkthrough | client-demo/google-cloud-aapl/Google_Cloud_AAPL_DeltaSignal_MCP_Client_Demo_2026_08_06.html; client-demo/google-cloud-aapl/test-interactive-walkthrough.mjs | #interactive-walkthrough | Client evaluator | As a client evaluator, I want direct stage selection so that I can inspect Source, Govern, Route, Delegate, Review, and Deliver in any order. | Six tabs activate the corresponding visual nodes, copy, evidence boundary, count, and progress state. | Observed behavior matched the tracker-backed expectation in the discovery test pass. | Verified | Automated UI | Count six tabs; click each; assert active class, aria-selected, stage title/copy/boundary/count, and live node states. | PASS — qa_evidence/logs/aapl-walkthrough-test.log; qa_evidence/logs/feature_ui_audit.json |  |  | No |  |  |  |  | Not required in discovery pass. | Verified | No | Discovery evidence: qa_evidence/logs/aapl-walkthrough-test.log; qa_evidence/logs/feature_ui_audit.json | /goal implement the cutting edge UI rich with graphics and easy to understand
AAPL-003 | Walkthrough back and next | AAPL Client Demo / Walkthrough | client-demo/google-cloud-aapl/Google_Cloud_AAPL_DeltaSignal_MCP_Client_Demo_2026_08_06.html; client-demo/google-cloud-aapl/test-interactive-walkthrough.mjs | #interactive-walkthrough | Demo viewer | As a demo viewer, I want Back and Next controls so that I can step through the evidence path sequentially. | Back/Next advance one stage and disable correctly at first/final stages. | Observed behavior matched the tracker-backed expectation in the discovery test pass. | Verified | Automated UI | Navigate first to last and back; assert counts, active stage, and disabled controls. | PASS — qa_evidence/logs/aapl-walkthrough-test.log; qa_evidence/logs/feature_ui_audit.json |  |  | No |  |  |  |  | Not required in discovery pass. | Verified | No | Discovery evidence: qa_evidence/logs/aapl-walkthrough-test.log; qa_evidence/logs/feature_ui_audit.json | /goal implement the cutting edge UI rich with graphics and easy to understand
AAPL-004 | Walkthrough reset | AAPL Client Demo / Walkthrough | client-demo/google-cloud-aapl/Google_Cloud_AAPL_DeltaSignal_MCP_Client_Demo_2026_08_06.html; client-demo/google-cloud-aapl/test-interactive-walkthrough.mjs | #interactive-walkthrough | Demo viewer | As a demo viewer, I want Reset so that I can restart a demonstration from Source. | Reset stops autoplay and restores stage 1, progress, copy, and active nodes. | Observed behavior matched the tracker-backed expectation in the discovery test pass. | Verified | Automated UI | Navigate to stage 4; start autoplay; click Reset; assert stage 1 and paused state. | PASS — qa_evidence/logs/aapl-walkthrough-test.log; qa_evidence/logs/feature_ui_audit.json |  |  | No |  |  |  |  | Not required in discovery pass. | Verified | No | Discovery evidence: qa_evidence/logs/aapl-walkthrough-test.log; qa_evidence/logs/feature_ui_audit.json | /goal implement the cutting edge UI rich with graphics and easy to understand
AAPL-005 | Walkthrough autoplay | AAPL Client Demo / Walkthrough | client-demo/google-cloud-aapl/Google_Cloud_AAPL_DeltaSignal_MCP_Client_Demo_2026_08_06.html; client-demo/google-cloud-aapl/test-interactive-walkthrough.mjs | #interactive-walkthrough | Presenter | As a presenter, I want autoplay so that the six-stage explanation can run hands-free. | Autoplay advances, can pause, updates its accessible label, and stops at the final stage. | Observed behavior matched the tracker-backed expectation in the discovery test pass. | Verified | Automated UI | Start autoplay; wait for stage 2; pause; verify label; resume to final and assert stop. | PASS — qa_evidence/logs/aapl-walkthrough-test.log; qa_evidence/logs/feature_ui_audit.json |  |  | No |  |  |  |  | Not required in discovery pass. | Verified | No | Discovery evidence: qa_evidence/logs/aapl-walkthrough-test.log; qa_evidence/logs/feature_ui_audit.json | /goal implement the cutting edge UI rich with graphics and easy to understand
AAPL-006 | Walkthrough presentation view | AAPL Client Demo / Presentation | client-demo/google-cloud-aapl/Google_Cloud_AAPL_DeltaSignal_MCP_Client_Demo_2026_08_06.html; client-demo/google-cloud-aapl/test-interactive-walkthrough.mjs | ?presentation=1 or Presentation view | Presenter | As a presenter, I want presentation mode so that I can record a focused walkthrough. | Button and query parameter activate presentation mode; Escape exits; desktop and mobile have no horizontal overflow. | Observed behavior matched the tracker-backed expectation in the discovery test pass. | Verified | Automated UI | Activate by button and query; inspect body class; press Escape; repeat at 390x844 and measure overflow. | PASS — qa_evidence/logs/aapl-walkthrough-test.log; qa_evidence/logs/feature_ui_audit.json |  |  | No |  |  |  |  | Not required in discovery pass. | Verified | No | Discovery evidence: qa_evidence/logs/aapl-walkthrough-test.log; qa_evidence/logs/feature_ui_audit.json | /goal implement the cutting edge UI rich with graphics and easy to understand
AAPL-007 | MCP call-path visualization | AAPL Client Demo / MCP | client-demo/google-cloud-aapl/Google_Cloud_AAPL_DeltaSignal_MCP_Client_Demo_2026_08_06.html; client-demo/google-cloud-aapl/test-interactive-walkthrough.mjs | #mcp-call-path | AI engineer | As an AI engineer, I want a concrete MCP request/response visualization so that I know what the Google Cloud coordinator sends and receives. | Visualization names coordinator, tool, AAPL ticker payload, evidence envelope, provenance boundary, and review path in readable form. | Observed behavior matched the tracker-backed expectation in the discovery test pass. | Verified | Automated UI | Inspect call-path text and graphics; assert coordinator, deltasignal_company_fundamentals, ticker AAPL, evidence envelope; capture screenshot. | PASS — qa_evidence/logs/aapl-walkthrough-test.log; qa_evidence/logs/feature_ui_audit.json |  |  | No |  |  |  |  | Not required in discovery pass. | Verified | No | Discovery evidence: qa_evidence/logs/aapl-walkthrough-test.log; qa_evidence/logs/feature_ui_audit.json | /goal implement the cutting edge UI rich with graphics and easy to understand
AAPL-008 | Evidence-boundary explanations | AAPL Client Demo / Trust | client-demo/google-cloud-aapl/Google_Cloud_AAPL_DeltaSignal_MCP_Client_Demo_2026_08_06.html; client-demo/google-cloud-aapl/test-interactive-walkthrough.mjs | #interactive-walkthrough | Financial analyst | As a financial analyst, I want each stage to state what it can and cannot prove so that I do not confuse evidence with interpretation. | Every stage has a distinct boundary statement; missing attribution and unavailable levels remain explicit. | Observed behavior matched the tracker-backed expectation in the discovery test pass. | Verified | Automated UI | Select each stage; record boundary text; assert nonempty and distinct; verify no unsupported trade or attribution claims. | PASS — qa_evidence/logs/aapl-walkthrough-test.log; qa_evidence/logs/feature_ui_audit.json |  |  | No |  |  |  |  | Not required in discovery pass. | Verified | No | Discovery evidence: qa_evidence/logs/aapl-walkthrough-test.log; qa_evidence/logs/feature_ui_audit.json | /goal implement the cutting edge UI rich with graphics and easy to understand
AAPL-009 | Demo resource actions | AAPL Client Demo / Resources | client-demo/google-cloud-aapl/Google_Cloud_AAPL_DeltaSignal_MCP_Client_Demo_2026_08_06.html; client-demo/google-cloud-aapl/test-interactive-walkthrough.mjs | Demo footer actions | Builder | As a builder, I want architecture, video scenario, MCP, and operator-contract links so that I can reproduce the workflow. | All resource actions are clearly labeled and resolve to valid targets. | Observed behavior matched the tracker-backed expectation in the discovery test pass. | Verified | Automated UI | Enumerate four resource links; validate hrefs and local 200 responses; inspect keyboard focus. | PASS — qa_evidence/logs/aapl-walkthrough-test.log; qa_evidence/logs/feature_ui_audit.json |  |  | No |  |  |  |  | Not required in discovery pass. | Verified | No | Discovery evidence: qa_evidence/logs/aapl-walkthrough-test.log; qa_evidence/logs/feature_ui_audit.json | /goal implement the cutting edge UI rich with graphics and easy to understand
AAPL-010 | Responsive AAPL demo | AAPL Client Demo / Cross-cutting | client-demo/google-cloud-aapl/Google_Cloud_AAPL_DeltaSignal_MCP_Client_Demo_2026_08_06.html; client-demo/google-cloud-aapl/test-interactive-walkthrough.mjs | Demo desktop and mobile | All visitors | As a visitor, I want the interactive demo to remain readable on desktop and mobile so that diagrams and controls are usable. | No horizontal overflow; controls wrap safely; text remains legible; presentation mode is usable at 390px and 1440px. | Observed behavior matched the tracker-backed expectation in the discovery test pass. | Verified | Automated UI | Measure overflow and control bounding boxes at 390x844, 1024x900, 1440x1000; run accessibility snapshot. | PASS — qa_evidence/logs/aapl-walkthrough-test.log; qa_evidence/logs/feature_ui_audit.json |  |  | No |  |  |  |  | Not required in discovery pass. | Verified | No | Discovery evidence: qa_evidence/logs/aapl-walkthrough-test.log; qa_evidence/logs/feature_ui_audit.json | /goal implement the cutting edge UI rich with graphics and easy to understand
CLOUD-001 | Cloud Run root landing | Cloud Run Web UI / Landing | cmd/server/demo_ui.go; cmd/server/demo_ui_test.go | GET / | Technical evaluator | As a technical evaluator, I want a concise service landing page so that I can open the browser demo or run the HUT proof. | Landing communicates agent-executable diligence, execution loop, runtime identity, TripCode, and two clear actions. | Root service page was reframed as DeltaSignal Evidence OS with Apple SEC/XBRL as stage one and HUT memory as a secondary action. | Fixed | Automated Test | Run cmd/server route tests; render root HTML locally; inspect required copy, graphics, links, and responsive layout. | FAIL — qa_evidence/screenshots/cloud-root-1440x1000.png ¦ FIX VERIFIED | Root landing still presents ‘Google for Startups AI Agents Challenge 2026 · Track 3’ and HUT as the product priority; this is stale competition framing. | High | Yes | Root service page was reframed as DeltaSignal Evidence OS with Apple SEC/XBRL as stage one and HUT memory as a secondary action. | cmd/server/demo_ui.go; cmd/server/demo_ui_test.go | 4883949 | Run cmd/server route tests; render root HTML locally; inspect required copy, graphics, links, and responsive layout. | PASS — desktop/mobile render without overflow; stale competition language absent; Apple and HUT roles explicit. | Verified | No | Pre-fix discovery evidence: qa_evidence/screenshots/cloud-root-1440x1000.png ¦ Retest evidence: qa_evidence/screenshots/cloud-root-1440x1000.png; qa_evidence/lighthouse/retest-cloud-root-desktop/report.json ¦ Stable pre-fix finding: qa_evidence/logs/discovery_findings.json | /goal implement the cutting edge UI rich with graphics and easy to understand
CLOUD-002 | Cloud Run demo landing | Cloud Run Web UI / Demo landing | cmd/server/demo_ui.go; cmd/server/demo_ui_test.go | GET /demo | Demo viewer | As a demo viewer, I want an animated HUT overview so that I understand how Substack research becomes agent-executable diligence. | Page presents HUT TripCode, architecture graphic, proof counts, Go action, two-minute demo action, and return path. | Demo landing now uses a complete architecture visual, sub-second reveal sequence, and explicit second-proof context. | Fixed | Automated Test | Run route test; render /demo; verify copy, SVG architecture, actions, responsive behavior, and non-advice framing. | FAIL — qa_evidence/screenshots/cloud-demo-1440x1000.png ¦ FIX VERIFIED | Demo landing is visually sparse after the narrow hero card, delays important controls behind long reveal animations, and retains stale competition branding. | High | Yes | Demo landing now uses a complete architecture visual, sub-second reveal sequence, and explicit second-proof context. | cmd/server/demo_ui.go; cmd/server/demo_ui_test.go | 4883949 | Run route test; render /demo; verify copy, SVG architecture, actions, responsive behavior, and non-advice framing. | PASS — first viewport is populated, readable, and visually explains User → Cloud Run → MCP/River/Evidence → packet. | Verified | No | Pre-fix discovery evidence: qa_evidence/screenshots/cloud-demo-1440x1000.png ¦ Retest evidence: qa_evidence/screenshots/cloud-demo-1440x1000.png ¦ Stable pre-fix finding: qa_evidence/logs/discovery_findings.json | /goal implement the cutting edge UI rich with graphics and easy to understand
CLOUD-003 | Cloud demo credentials and identifiers | Cloud Run Web UI / Inputs | cmd/server/demo_ui.go; cmd/server/demo_ui_test.go | GET /demo/run | Authorized demo operator | As an authorized operator, I want to enter a demo key, TripCode, and session ID so that protected requests use my intended context. | Inputs are labeled, preserve password secrecy, contain safe defaults only for public identifiers, and are included in requests correctly. | Observed behavior matched the tracker-backed expectation in the discovery test pass. | Verified | Automated Test | Render /demo/run; inspect labels/types/defaults; enter values; intercept request headers/query/body and verify propagation without logging secrets. | PASS — qa_evidence/logs/go-test-all.log; qa_evidence/logs/feature_ui_audit.json |  |  | No |  |  |  |  | Not required in discovery pass. | Verified | No | Discovery evidence: qa_evidence/logs/go-test-all.log; qa_evidence/logs/feature_ui_audit.json | /goal implement the cutting edge UI rich with graphics and easy to understand
CLOUD-004 | Overview and article modes | Cloud Run Web UI / Response | cmd/server/demo_ui.go; cmd/server/demo_ui_test.go | /demo/run Overview and Article | Demo viewer | As a demo viewer, I want overview and article modes so that I understand the workflow before making live requests. | Overview explains expected sequence; Article displays the public HUT article context and a safe external link. | Observed behavior matched the tracker-backed expectation in the discovery test pass. | Verified | Automated Test | Activate Overview and Article; verify response content, article image/link, no network mutation, and selected-action feedback. | PASS — qa_evidence/logs/go-test-all.log; qa_evidence/logs/feature_ui_audit.json |  |  | No |  |  |  |  | Not required in discovery pass. | Verified | No | Discovery evidence: qa_evidence/logs/go-test-all.log; qa_evidence/logs/feature_ui_audit.json | /goal implement the cutting edge UI rich with graphics and easy to understand
CLOUD-005 | Health and agent discovery | Cloud Run Web UI / Diagnostics | cmd/server/demo_ui.go; cmd/server/demo_ui_test.go | /demo/run Health and Card | Agent builder | As an agent builder, I want health and Agent Card controls so that I can verify service readiness and discover capabilities. | Health requests /health and Card requests the public Agent Card; loading, success, error, and JSON presentation are visible. | Observed behavior matched the tracker-backed expectation in the discovery test pass. | Verified | Automated Test | Run local server; click Health and Card; verify request routes, loading state, response title, JSON syntax display, and failure behavior. | PASS — qa_evidence/logs/go-test-all.log; qa_evidence/logs/feature_ui_audit.json |  |  | No |  |  |  |  | Not required in discovery pass. | Verified | No | Discovery evidence: qa_evidence/logs/go-test-all.log; qa_evidence/logs/feature_ui_audit.json | /goal implement the cutting edge UI rich with graphics and easy to understand
CLOUD-006 | TripCode resolve | Cloud Run Web UI / Research | cmd/server/demo_ui.go; cmd/server/demo_ui_test.go | /demo/run Resolve | Financial researcher | As a researcher, I want to resolve a HUT TripCode so that I can inspect article memory, River continuity, and evidence boundaries. | Resolve sends encoded TripCode/session/issuer options, displays request trace and result, preserves missing/live errors, and never fabricates evidence. | Observed behavior matched the tracker-backed expectation in the discovery test pass. | Verified | Automated Test | Intercept Resolve request; verify query; test success, 4xx, malformed JSON, and network failure; inspect rich and JSON output. | PASS — qa_evidence/logs/go-test-all.log; qa_evidence/logs/feature_ui_audit.json |  |  | No |  |  |  |  | Not required in discovery pass. | Verified | No | Discovery evidence: qa_evidence/logs/go-test-all.log; qa_evidence/logs/feature_ui_audit.json | /goal implement the cutting edge UI rich with graphics and easy to understand
CLOUD-007 | A2A resolve and monitor | Cloud Run Web UI / A2A | cmd/server/demo_ui.go; cmd/server/demo_ui_test.go | /demo/run A2A and Monitor | Agent integrator | As an agent integrator, I want A2A resolve and monitor controls so that I can invoke discoverable research skills and inspect task packets. | JSON-RPC requests contain correct methods, message text, and session metadata; result and error packets remain inspectable. | Observed behavior matched the tracker-backed expectation in the discovery test pass. | Verified | Automated Test | Intercept A2A and Monitor POST bodies; verify JSON-RPC shape; test success/error; inspect displayed task status and provenance. | PASS — qa_evidence/logs/go-test-all.log; qa_evidence/logs/feature_ui_audit.json |  |  | No |  |  |  |  | Not required in discovery pass. | Verified | No | Discovery evidence: qa_evidence/logs/go-test-all.log; qa_evidence/logs/feature_ui_audit.json | /goal implement the cutting edge UI rich with graphics and easy to understand
CLOUD-008 | Usage visibility | Cloud Run Web UI / Usage | cmd/server/demo_ui.go; cmd/server/demo_ui_test.go | /demo/run Usage | Demo operator | As a demo operator, I want usage visibility so that I can inspect request accounting and cost metadata. | Usage calls /v1/usage with authorization context and renders returned accounting without inventing billing data. | Observed behavior matched the tracker-backed expectation in the discovery test pass. | Verified | Automated Test | Activate Usage; intercept request; return fixture usage; verify labels and null/missing handling. | PASS — qa_evidence/logs/go-test-all.log; qa_evidence/logs/feature_ui_audit.json |  |  | No |  |  |  |  | Not required in discovery pass. | Verified | No | Discovery evidence: qa_evidence/logs/go-test-all.log; qa_evidence/logs/feature_ui_audit.json | /goal implement the cutting edge UI rich with graphics and easy to understand
CLOUD-009 | Response navigation and render modes | Cloud Run Web UI / Response tools | cmd/server/demo_ui.go; cmd/server/demo_ui_test.go | /demo/run response controls | Demo viewer | As a demo viewer, I want Top, Scroll, End, Render, and JSON controls so that I can inspect long responses in useful forms. | Navigation moves the response viewport; Render and JSON switch representations without losing the preserved raw packet. | Observed behavior matched the tracker-backed expectation in the discovery test pass. | Verified | Automated Test | Load long fixture; activate navigation controls; inspect scroll positions; toggle rich/JSON twice; verify content preservation and active state. | PASS — qa_evidence/logs/go-test-all.log; qa_evidence/logs/feature_ui_audit.json |  |  | No |  |  |  |  | Not required in discovery pass. | Verified | No | Discovery evidence: qa_evidence/logs/go-test-all.log; qa_evidence/logs/feature_ui_audit.json | /goal implement the cutting edge UI rich with graphics and easy to understand
CLOUD-010 | Automated two-minute sequence | Cloud Run Web UI / Demo automation | cmd/server/demo_ui.go; cmd/server/demo_ui_test.go | /demo/run?autoplay=1 | Presenter | As a presenter, I want an automated two-minute sequence so that I can demonstrate the complete workflow consistently. | Autoplay activates the intended ordered controls, exposes explanatory captions, supports interruption, and does not send uncontrolled payments. | Observed behavior matched the tracker-backed expectation in the discovery test pass. | Verified | Automated Test | Load autoplay query with mocked fetch; record action order/timing/captions; interrupt; assert no payment or destructive calls. | PASS — qa_evidence/logs/go-test-all.log; qa_evidence/logs/feature_ui_audit.json |  |  | No |  |  |  |  | Not required in discovery pass. | Verified | No | Discovery evidence: qa_evidence/logs/go-test-all.log; qa_evidence/logs/feature_ui_audit.json | /goal implement the cutting edge UI rich with graphics and easy to understand
CLOUD-011 | Cloud demo access and failure states | Cloud Run Web UI / Errors | cmd/server/demo_ui.go; cmd/server/demo_ui_test.go | /demo/run protected requests | Demo viewer | As a demo viewer, I want clear access and failure states so that I know whether a request needs authorization, payment, or retry. | 401/402/403/404/500/network failures are labeled distinctly, preserve returned details, and never present fallback data as live evidence. | Observed behavior matched the tracker-backed expectation in the discovery test pass. | Verified | Automated Test | Mock each status and network failure for Resolve/A2A/Usage; inspect title, body, provenance, retry affordance, and absence of false success. | PASS — qa_evidence/logs/go-test-all.log; qa_evidence/logs/feature_ui_audit.json |  |  | No |  |  |  |  | Not required in discovery pass. | Verified | No | Discovery evidence: qa_evidence/logs/go-test-all.log; qa_evidence/logs/feature_ui_audit.json | /goal implement the cutting edge UI rich with graphics and easy to understand
CLOUD-012 | Cloud web UI responsive accessibility | Cloud Run Web UI / Cross-cutting | cmd/server/demo_ui.go; cmd/server/demo_ui_test.go | /, /demo, /demo/run | All visitors | As a visitor, I want the Cloud Run pages to work on mobile, keyboard, and assistive technology so that I can inspect the demo reliably. | Pages have landmarks, labels, visible focus, sufficient contrast, no horizontal overflow, and motion-safe behavior. | Mobile CSS now removes fixed-width constraints, uses minmax grid tracks, contains decorative overflow, and stacks operator fields. | Fixed | Manual UI | Run local server; test three routes at desktop/mobile; keyboard through controls; Lighthouse snapshot; reduced-motion inspection. | FAIL — qa_evidence/screenshots/cloud-run-390x844.png ¦ FIX VERIFIED | The /demo/run interface is wider than the 390px viewport while horizontal overflow is suppressed, clipping headings, explanatory copy, inputs, and controls. | Critical | Yes | Mobile CSS now removes fixed-width constraints, uses minmax grid tracks, contains decorative overflow, and stacks operator fields. | cmd/server/demo_ui.go; cmd/server/demo_ui_test.go | 4883949 | Run local server; test three routes at desktop/mobile; keyboard through controls; Lighthouse snapshot; reduced-motion inspection. | PASS — 390px viewport has innerWidth=390, document/body scrollWidth=390, and an uncropped full-page screenshot. | Verified | No | Pre-fix discovery evidence: qa_evidence/screenshots/cloud-run-390x844.png ¦ Retest evidence: qa_evidence/screenshots/retest-cloud-run-390x844.png; qa_evidence/logs/retest-go-server.log ¦ Stable pre-fix finding: qa_evidence/logs/discovery_findings.json | /goal implement the cutting edge UI rich with graphics and easy to understand
API-001 | Service readiness | Public API / Health | cmd/server/main.go; cmd/server/main_test.go | GET /health and /healthz | Agent integrator | As an integrator, I want a readiness response so that I can determine whether the service is available before invoking research. | Both routes return bounded JSON readiness with correct status and no secret leakage. | Observed behavior matched the tracker-backed expectation in the discovery test pass. | Verified | Automated Test | Run Go handler tests; call routes; validate status/content type/schema and secret absence. | PASS — qa_evidence/logs/go-test-all.log |  |  | No |  |  |  |  | Not required in discovery pass. | Verified | No | Discovery evidence: qa_evidence/logs/go-test-all.log | /goal implement the cutting edge UI rich with graphics and easy to understand
API-002 | Agent Card discovery | Public API / A2A | cmd/server/a2a.go; cmd/server/a2a_test.go | GET /.well-known/agent-card.json | Agent integrator | As an agent integrator, I want an Agent Card so that I can discover supported skills and invoke the correct A2A endpoint. | Card returns protocol version, public URL, skills, security scheme, input/output modes, and evidence boundaries. | Observed behavior matched the tracker-backed expectation in the discovery test pass. | Verified | Automated Test | Run A2A tests; GET both card paths; validate schema fields, URLs, skills, and forwarded-host safety. | PASS — qa_evidence/logs/go-test-all.log |  |  | No |  |  |  |  | Not required in discovery pass. | Verified | No | Discovery evidence: qa_evidence/logs/go-test-all.log | /goal implement the cutting edge UI rich with graphics and easy to understand
API-003 | Issuer action brief | Public API / Brief | cmd/server/main.go; cmd/server/main_test.go; internal/agent | POST /v1/brief | Financial analyst | As an analyst, I want an issuer action brief so that I can identify evidence-backed diligence questions without receiving investment advice. | Valid issuer request returns evidence-preserving brief; invalid JSON/issuer returns clear errors; provenance and non-advice boundary remain present. | Observed behavior matched the tracker-backed expectation in the discovery test pass. | Verified | Automated Test | Run handler and agent tests; submit valid/empty/malformed requests; validate statuses, evidence fields, caveats, and prohibited-language absence. | PASS — qa_evidence/logs/go-test-all.log |  |  | No |  |  |  |  | Not required in discovery pass. | Verified | No | Discovery evidence: qa_evidence/logs/go-test-all.log | /goal implement the cutting edge UI rich with graphics and easy to understand
API-004 | TripCode research memory | Public API / TripCode | cmd/server/main.go; cmd/server/main_test.go; internal/agent | POST /v1/tripcode and GET/POST /resolve | Subscriber researcher | As a subscriber researcher, I want to resolve and continue a TripCode session so that I can compare thesis history and monitor changes. | Resolve supports initial TripCode and follow-up session questions, preserves River/evidence/missingness, and handles unavailable public MCP honestly. | Observed behavior matched the tracker-backed expectation in the discovery test pass. | Verified | Automated Test | Run TripCode and resolve tests; exercise initial/follow-up/missing/malformed cases; verify session continuity and fallback disclosure. | PASS — qa_evidence/logs/go-test-all.log |  |  | No |  |  |  |  | Not required in discovery pass. | Verified | No | Discovery evidence: qa_evidence/logs/go-test-all.log | /goal implement the cutting edge UI rich with graphics and easy to understand
API-005 | A2A message execution | Public API / A2A | cmd/server/a2a.go; cmd/server/a2a_test.go | POST /a2a | External agent | As an external agent, I want to send a discoverable A2A message so that I can receive a structured research task result. | Supported methods return JSON-RPC task packets; invalid methods/input/auth return protocol-correct errors without losing evidence boundaries. | Observed behavior matched the tracker-backed expectation in the discovery test pass. | Verified | Automated Test | Run A2A handler tests; send resolve/monitor/invalid requests; validate JSON-RPC IDs, statuses, artifacts, and errors. | PASS — qa_evidence/logs/go-test-all.log |  |  | No |  |  |  |  | Not required in discovery pass. | Verified | No | Discovery evidence: qa_evidence/logs/go-test-all.log | /goal implement the cutting edge UI rich with graphics and easy to understand
API-006 | Scenario discovery and execution | Public API / Scenarios | cmd/server/scenario.go; cmd/server/scenario_test.go; internal/agent/scenario.go | GET /v1/scenarios; POST /v1/scenarios/run | Demo operator | As a demo operator, I want discoverable scenarios so that I can run a deterministic end-to-end workflow. | List returns available scenarios; run validates IDs/input, executes expected steps, preserves errors and provenance, and reports result state. | Observed behavior matched the tracker-backed expectation in the discovery test pass. | Verified | Automated Test | Run scenario tests; list; run valid/missing/malformed/failure scenarios; validate status and step outputs. | PASS — qa_evidence/logs/go-test-all.log |  |  | No |  |  |  |  | Not required in discovery pass. | Verified | No | Discovery evidence: qa_evidence/logs/go-test-all.log | /goal implement the cutting edge UI rich with graphics and easy to understand
API-007 | Usage and cost metadata | Public API / Usage | cmd/server/main.go; cmd/server/main_test.go; internal/agent/cost_tracker.go | GET /v1/usage | Operator | As an operator, I want usage metadata so that I can understand request and model-cost accounting. | Authorized route reports recorded usage accurately, handles disabled/unauthorized state, and does not imply payment settlement. | Observed behavior matched the tracker-backed expectation in the discovery test pass. | Verified | Automated Test | Run cost/handler tests; test configured/unconfigured/unauthorized; compare totals with known fixture events. | PASS — qa_evidence/logs/go-test-all.log |  |  | No |  |  |  |  | Not required in discovery pass. | Verified | No | Discovery evidence: qa_evidence/logs/go-test-all.log | /goal implement the cutting edge UI rich with graphics and easy to understand
API-008 | Product-loop workflow | Public API / Product Loop | cmd/server/main.go; cmd/server/main_test.go; internal/agent/product_loop.go | POST /v1/product-loop | Agent workflow operator | As an operator, I want a governed product loop so that builders and reviewers can execute a bounded implementation workflow. | Request validates objective/workflow/risk, returns structured plan/results, preserves approval boundaries, and surfaces failures. | Observed behavior matched the tracker-backed expectation in the discovery test pass. | Verified | Automated Test | Run product-loop tests; submit valid/empty/malformed/high-risk requests; inspect response stages, approvals, and errors. | PASS — qa_evidence/logs/go-test-all.log |  |  | No |  |  |  |  | Not required in discovery pass. | Verified | No | Discovery evidence: qa_evidence/logs/go-test-all.log | /goal implement the cutting edge UI rich with graphics and easy to understand
DOC-001 | Architecture visual specification | Documentation | docs/DeltaSignal_Daily_Backend_to_Google_Agents_Architecture_2026_08_06.html | Architecture link | Technical evaluator | As a technical evaluator, I want a detailed visual architecture so that I can inspect daily ingestion, MCP routing, agents, and boundaries. | Self-contained visual loads without clipping, has readable labels, embedded contract, source boundaries, and links back to relevant product context. | Observed behavior matched the tracker-backed expectation in the discovery test pass. | Verified | Manual UI | Open document desktop/mobile; inspect diagram fit, typography, contract presence, and no horizontal clipping; Lighthouse snapshot. | PASS — qa_evidence/logs/feature_ui_audit.json |  |  | No |  |  |  |  | Not required in discovery pass. | Verified | No | Discovery evidence: qa_evidence/logs/feature_ui_audit.json | /goal implement the cutting edge UI rich with graphics and easy to understand
DOC-002 | Three-minute video scenario | Documentation | docs/Google_Cloud_AAPL_MCP_Three_Minute_Video_Scenario_2026_08_06.html | Recording plan link | Content producer | As a content producer, I want a timed recording plan so that I can demonstrate the AAPL workflow accurately in three minutes. | Scenario has ordered timing, narration, on-screen actions, evidence boundaries, and valid demo links. | Observed behavior matched the tracker-backed expectation in the discovery test pass. | Verified | Code Review | Inspect sections, timing totals, links, and consistency with current UI; verify no obsolete competition-only framing. | PASS — qa_evidence/logs/feature_ui_audit.json |  |  | No |  |  |  |  | Not required in discovery pass. | Verified | No | Discovery evidence: qa_evidence/logs/feature_ui_audit.json | /goal implement the cutting edge UI rich with graphics and easy to understand
DOC-003 | Comprehension audit receipt | Documentation | docs/DeltaSignal_First_10_Seconds_Comprehension_Audit_2026_08_07.html | Footer audit link | Prospective buyer | As a prospective buyer, I want to inspect the comprehension audit so that I can see what was tested and the limits of the 100% result. | Audit clearly labels simulation boundary, three rounds, persona scores, fixes, runtime receipt, and embedded XML; scores are not presented as human research. | Observed behavior matched the tracker-backed expectation in the discovery test pass. | Verified | Automated UI | Load document; assert key boundary/result/provenance text; inspect responsive layout; Lighthouse accessibility/best-practices. | PASS — qa_evidence/logs/feature_ui_audit.json |  |  | No |  |  |  |  | Not required in discovery pass. | Verified | No | Discovery evidence: qa_evidence/logs/feature_ui_audit.json | /goal implement the cutting edge UI rich with graphics and easy to understand
WEB-018 | Top-level project description | Landing / Hero | index.html; tests/landing-page.mjs | / first viewport | First-time visitor | As a first-time visitor, I want a plain-language project description at the top so that I immediately understand what DeltaSignal is, what evidence it uses, and who it serves. | A visible description above the Apple reference identifies DeltaSignal as a governed financial-evidence operating system that turns dated filings and market data into provenance-rich research packets for AI agents and human analysts. | The project description is visible above the Apple case, uses concise plain language, and remains readable on desktop and mobile. | Verified | Automated UI | Load /; inspect the first viewport; assert the four defining phrases; verify visibility; rerun desktop and mobile landing tests. | PASS — qa_evidence/logs/project-description-test.log |  |  | No |  | index.html; tests/landing-page.mjs; CHANGELOG.html | 9530d6a | Run node tests/landing-page.mjs. | PASS — landing-page: PASS | Verified | No | Added after the completed 55-story audit as the next tracker-backed homepage enhancement. | at the top add description of the project
WEB-019 | Daily SEC-to-MCP-to-Google-agents explanation | Landing / Hero | index.html; tests/landing-page.mjs | / first viewport | First-time visitor / prospective client | As a first-time visitor, I want to see how DeltaSignal turns daily SEC evidence into an MCP-accessible database and how Google agents use it for Apple, so that I understand the product before opening the demo. | The first viewport shows four ordered and visible stages: collect public SEC/EDGAR and CompanyFacts/XBRL evidence; normalize, validate, date, hash, and materialize it in a governed evidence database; deliver bounded provenance-rich envelopes through read-only DeltaSignal MCP tools; and route AAPL questions through a Cloud Run coordinator to four bounded Google Cloud specialists without allowing Gemini explanation to replace source evidence. | The homepage now presents the complete daily SEC → governed evidence database → DeltaSignal MCP → Apple × Google Cloud agents sequence above the Apple reference case on desktop and mobile. | Verified | Automated UI | Load / on desktop and mobile; assert the workflow is visible; assert exactly four stages and all required SEC, database, MCP, Cloud Run, specialist-agent, and evidence-boundary phrases; verify no mobile horizontal overflow. | PASS — qa_evidence/logs/daily-sec-mcp-google-agents-test.log |  |  | No | Added a four-stage visual operating model and supporting automated assertions. | index.html; tests/landing-page.mjs; CHANGELOG.html | 220ee75 | Run node tests/landing-page.mjs. | PASS — landing-page: PASS | Verified | No | Claims are bounded to the documented daily backend and Google Cloud AAPL client architecture; no claim that model-generated explanation replaces evidence. | add description how deltasignal works every day collecting SEC information , creating db making it available to MCP, then describe how MCP is used in this example with Apple by creating ther agrents in google

## Dashboard
Feature QA Audit Dashboard
Metric | Value | Severity | Open Count
Tracked Features | 57 | Critical | 0
Current Verified | 51 | High | 0
Failed Test | 0 | Medium | 0
Fix In Progress | 0 | Low | 0
Fixed | 6 | Needs Product Decision | 0
Final Verified | 57 | Rows With Commit Hash | 8
Blocked | 0
Use Tracker as the working sheet. Dashboard values are calculated during generation and exported as a portable snapshot.

## Lists
Allowed Status | Allowed Severity | Suggested Test Type
Not Reviewed | Critical | Code Review
Story Drafted | High | Manual UI
Ready For Test | Medium | Automated Test
Failed Test | Low | Smoke Test
Fix In Progress | None | Regression Test
Fixed |  | Accessibility Review
Retest Failed |  | Responsive Review
Verified |  | Integration Test
Blocked
Needs Product Decision

## Instructions
Feature QA Workbook Guide
Step | Instruction
1 | Keep Tracker as the single source of truth and do not create competing trackers.
2 | Create one row per user-visible feature or critical behavior. User stories describe how a user uses the feature, not how the implementation works.
3 | Use Status during discovery and testing, then use Final Status after retest.
4 | Record commit hashes in column S for any row touched by a fix or follow-up pass.
5 | Use Lists sheet values for Status, Severity, Test Type, and Final Status to keep reporting clean.
6 | Append a dated note to CHANGELOG.md after each completed QA or improvement pass.
7 | Keep the CSV, XLSX, and HTML companion aligned after every tracker update.
8 | Open the Dashboard tab for a quick pass/fail snapshot before closing the loop.